## Avancement
Sprint 1
US | Cplx | T1 | Status | T2 | Status | Status |  | J0 | J1 | J2 | J3 | J4
#200 | 5 | 2 | In process | 3 | In process | To do | Théorique | 43 | 32.25 | 21.5 | 10.75 | 0
#300 | 3 | 2 | In process | 1 | To verify | In process | Réel | 43 | 43 | 43 | 43 | 43
#400 | 8 | 4 | In process | 4 | In process | To verify
#500 | 2 | 2 | To do |  |  | Done
#1000 | 5 | 2 | In process | 3 | In process
#1100 | 5 | 5 | To do
#1200 | 3 | 2 | In process | 1 | In process
#1300 | 8 | 4 | In process | 4 | In process
#1500 | 2 | 2 | To do
#1600 | 2 | 2 | To do
Total | 43